## High Level Project Roadmap
Comprehensive Program Backlog (Full Team) Subteam 1 Program Backlog ¦ Subteam 2 Program Backlog ¦ Subteam 3 Program Backlog | Project Roadmap
| Milestone 1 | [5 empty] | Milestone 2 | [6 empty] | Milestone 3 | [6 empty] | Milestone 4
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | RELEASE 1 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | RELEASE 2 | W19 | W20 | W21 | W22 | W23 | W24 | RELEASE 3
US01: Progress Save and Resume Feature for Puzzles | bar: Milestone 1 W1
US03: Difficulty Adjustment | bar: Milestone 1 W2
US08: Word Puzzles | bar: Milestone 1 W4
US11: Player creates account | bar: Milestone 1 W5
US12: Time Recorded for Each Game | bar: Milestone 1 W6
US02: Shareable Player Leaderboards | bar: Milestone 2 W7 to Milestone 2 W8
US04: Hint System for Puzzles | bar: Milestone 2 W7 to Milestone 2 W8
US06: Seamless Puzzle Navigation Experience | bar: Milestone 2 W8 to Milestone 2 W9
US08: Word Puzzles | bar: Milestone 2 W9 to Milestone 2 W10
US09: Math Puzzles
US15: Admin account
NFR1: Intutive and Simplistic UI | bar: Milestone 2 W7 to Milestone 2 W9
NFR2: Secure data storage | bar: Milestone 2 W10
NFR3: Users can login as guests without an account
US05: Option to View Solution After Unsuccessful Attempts
US13: Achievement System and Reward System
US07: Logic Puzzles
NFR4: Attractive animation on Homepage
NFR5: Support 35 online users simultaneously
US10: Spatial Reasoning Puzzles
US14: Online Multiplayer Functionality
NFR6: Users can use the web app on phones, iPads, and PCs.
NFR7: Special aids for users with disabilities